## Sheet1
Defect Id | Detected in Cycle | Build Sequence | Test Phase | Detected in Release | Detected on Date | Detected By | Assigned To | Actual Fix Time (Hrs) | Business/Functionality | Closing Date | Description | Environment | Modified | Priority | Reason Code | Reproducible | Request Type | Severity | Status | Summary
1 | Cycle 2 |  | System Testing | Release 1 | 2021-09-07 | Saanya Dhir |  | 4 | UniformStore_Admin_AddProducts | 2021-09-08 | Price field not mandatory. | QA | 2021-09-07 17:00 | 1-Medium | Coding Errors | Y | Defect | 1-Medium |  | While adding a new product, price field is not mandatory.
2 | Cycle 2 |  | System Testing | Release 1 | 2021-09-07 | Saanya Dhir |  | 4 | UniformStore_Admin_AddProducts | 2021-09-08 | Quantity field not mandatory. | QA | 2021-09-07 17:00 | 1-Medium | Coding Errors | Y | Defect | 1-Medium |  | While adding a new product, quantity field is not mandatory.
3 | Cycle 2 |  | System Testing | Release 1 | 2021-09-07 | Saanya Dhir |  | 4 | UniformStore_Admin_AddProducts | 2021-09-08 | Manufacturer field not mandatory. | QA | 2021-09-07 17:00 | 1-Medium | Coding Errors | Y | Defect | 1-Medium |  | While adding a new product, manufacturer details are not mandatory.