## Sheet1
Test case and execution status tracking
Project: Uniform Store
Sr. No. | Module | No. of Test Cases | Date | Estimated Effort | Actual Effort | Reason for variance(if any)
1 | Add Products (Admin) | 3 | 04-08-2021 | 30m | 45m | N/A
2 | Update Products (Admin) | 3 | 04-05-2021 | 30m | 40m | N/A
3 | Delete Products (Admin) | 1 | 04-05-2021 | 30m | 30m | N/A
4 | Search Products (Admin) | 5 | 04-05-2021 | 20m | 25m | N/A